## Westerfield Action Plan

| ACTION | REASON | OWNER | PARTNERS | PRIORITY | DETAILS |
| --- | --- | --- | --- | --- | --- |
| 8.2 Utility Services |  |  |  |  |  |
| Connect households to Main drainage(Not Active) | Individual householders requests. | Val Byrne | Anglian Water (AW) | M | AW provided information pack with cost estimate. It has to be done on individual basis. Contact 01473 251843 for loan of pack. |
| Availability of mains Gas to village.(Not Active) | 72% of residents wish to be connected. Escalating cost of oil. | Val Byrne | Transco Parish Council | H | Transco provided information. Confirmed there are enough households interested to justify provision. Cost estimate is nearly £4000.00 per household.. |
| Eliminate surface water problems. | Responding to households with these problems. | Parish Council | Anglian Water. County Council. Residents affected | M | Not a new problem. Obtain results of previous investigations. New initiative may be needed to solve this. Monitor |
| 8.3 Housing |  |  |  |  |  |
| Relay results of housing survey to council. (Not Active) | Housing survey reflects the desires of the residents. | Parish Council | District Council | H |  |
| Use results to influence the new SCDC plan. | Housing survey reflects the desires of the residents. | Parish Council | District Council | H | Copy of parish plan sent to SCDC. Results are consistent with current local plan. New LDF being produced. Issues and Options consultation completed. |
| Opposition to Northern Fringe Development. | Only 6% of residents in favour of planned development. | Residents Action Group | Ipswich Borough Council. Parish Council. | H | New Ipswich development framework (LDF) shows production of following relevant documents. Core strategy/Site allocations-public consultation starts Sept 2007 with independent examination March 2008. Northern Fringe Development Brief-public consultation starts Dec 2008. Adoption of Northern Fringe Plan Apr 2009. Note number of proposed houses not yet stated. Parish Council have written to Ipswich BC showing results of village survey. |
| Opposition to Care Home (Not Active_ | Residents complain of noise. Lack of consultation. Unsuitability of location. | Parish Council | District Council. Residents affected | M |  |
| 8.4/5 Community Services |  |  |  |  |  |
| Increase police awareness in Westerfield | Lack of awareness of community police officer. Service provided felt to be poor. | Parish Council | Police | M | Feed back results to police and discuss ways of improving the situation. Community officer regularly attends parish council meetings to give updates. |
| Re-establish Neighbourhood Watch Scheme. | 75% of residents supported the idea. Crime in the area. | NW committee | Suffolk NW Association. Village Residents | M | Currently no volunteers to set up scheme. Cynthia Reeve had discussion with police, but need 7 volunteers plus co-ordinator to generate public meeting with police. Not enough volunteers from the village.. Parish Council pursuing the ‘Police Direct’ initiative. Individuals can register for regular police updates via email etc. Scheme now ceased due to lack of funding. |
| Increase waste collection facilities. | 93% of residents in favour. | Parish Council | District Council | M | More re-cycling collection schemes shortly to be introduced by SCDC. |
| Provide more ‘waste banks’. | Response to residents wishes. | Parish Council | District Council | H | Paper bank in village hall car park. Bottle bank in railway car park. |

| Establish ‘Good Neighbour Scheme’.(Not Active) | Response to residents wishes. An ad-hoc scheme already exists. | Residents Group | Suffolk Acre | M | Informal scheme already exists. Carry on with current informal scheme. |
| --- | --- | --- | --- | --- | --- |
| Establish Local Market (Not Active) | Survey indicates around 100 residents would attend. | Residents Group |  | L | No owner at present. Investigate occasional small Saturday market/coffee morning. See how it develops. |
| 8.6 Transport |  |  |  |  |  |
| Publicise up-to-date bus timetables | Supported by 30% of residents. More people might use service. | Cynthia Reeve | Bus Company Village Network | H | Timetable delivered to every household. Action complete. |
| Car/Cycle park at railway station. (Not Active) |  | Parish Council | Railway Pub. County/ Parish Council | M | Only 18% (8%) wanted car(cycle) park. Investigate possibility of using pub car park. |
| Opposition to moving station. (Not Active) | 88% of residents voted against the proposal in the Ipswich Plan | Northern Fringe Action Group | Ipswich Borough Council. Network Rail | H | Copy of parish plan given to Ipswich BC. Proposal withdrawn, awaiting detailed LDF plan from IBC. |
| 8.7 Traffic and Safety |  |  |  |  |  |
| Reduce traffic speed | 80% of residents think speeding is a problem. | Traffic and Safety Group. | Parish Council. County Council. Police | H | Introduce effective traffic calming measures. Had initial discussions with County Council. No funds are currently available. PC established possible funding for calming measures on Church Lane and Lower Road. PC commissioned relevant plans. CC investigating putting carriage roundels on main road. Monitor speed checks. |
| Introduce weight /size restrictions on minor roads. (Not Active) | Residents anxiety over congestion and heavy vehicles | Traffic and Safety Group | County Council | M | Restrict heavy vehicles using Church Lane and Lower Road. CC said putting weight restrictions is not that straightforward Suggested we monitor and report examples to CC. They will then contact perpetrators. |
| Eliminate danger spots. | Residents identified crossroads, blind summit on Church Lane, Moss Lane junction, and Henley Rd junction. | Traffic and Safety Group | Parish Council County Council | M | CC agreed crossroads is a danger spot and will investigate improvement. |
| Review adequacy of road signs. (Not Active) | 50-50 split on whether residents think improvement are needed. | Traffic and Safety Group | Parish Council County Council | L | Discuss survey suggestions with CC. |
| Improve pedestrian facilities. | Two thirds of residents think current facilities are poor. | Traffic and Safety Group | County Council Parish Council | H | Seek new pavements/pedestrian access routes. New pavements formally requested to CC, awaiting analysis and prioritisation. Low cost ‘white line’ scheme along Lower Road investigated by CC. Unfortunately too many places where road is not wide enough or too near ditches. Not recommended by CC. No funding available at present. |
| Improve cycling facilities. (Not Active) | Those that cycle think they are poor. | Traffic and Safety Group | County Council Parish Council | M | Introduce Cycle lanes on Nat Cycle route through village. |
| Improve street lighting (Not Active) | More than 50% of residents would like more lighting. | Traffic and Safety Group | County Council Parish Council | L | Identify locations. Consider environmentally friendly option. |

| Review speed limit boundaries | Help reduce speeding in village. Comments from residents | Traffic and Safety Group | County Council Parish Council | H | Extend speed limit sign on Church Lane to boundary sign past Moss lane junction. CC agreed to extend 30mph limit at top of Church Lane. This has now been completed. Relax 30mph limit between Westerfield and Valley Road. CC to contact Ipswich BC for Justification in introducing restriction. Ipswich agreed we have a case-It’s with their legal people preparing The order for advertising. |
| --- | --- | --- | --- | --- | --- |
| 8.8 Local Environment |  |  |  |  |  |
| Reduce traffic noise. Reduce train noise. Reduce aircraft noise. | Identified disturbances. | Traffic Group. Carol Easton. Parish Council | County Council Network Rail RAF Wattisham | H H L | CC have recognised concerns over volumes of traffic, particularly along east-west route. Suggested we wait to see effect of the Humber Doucy traffic scheme. Concerns over increased overnight trains. Invite RAF/civil to PC meeting. |
| Protect landscape and wildlife (Not Active) | Strong support from residents | Environmental Action Group | Various external environmental groups | M | Residents have volunteered to help. Contact Suffolk Wildlife Trust for advice. Set up improvement programme. Currently no leader for group. |
| Improve local footpaths and grass verges | 78% of respondents think local authority should undertake improvements. | Parish Council | County Council | M |  |
| Improve Village Hall car park. | Improvement suggested in survey. | Village Hall Trust | None. | M | New hard standing entrance to car park. |
| More Litter bins (Not Active) | Improvement suggested in survey. | Parish Council | None | M | Situation reviewed. Decided not to introduce more bins at present. |
| Remove litter. | 70% think removing litter would make village more attractive. | Environmental action group | None. | H | Organise litter picking days. First event was on April 22 2006. Event was very successful. Process fully in place-need volunteer to organise future events. |
| Produce local footpath map | Service to residents. | Parish Council | None. |  | ACHIEVED |
| Oppose proposed closure of level crossing. (Not Active) | 93% of residents are against closure. | Northern Fringe Action Group | Ipswich Borough Council |  | Inform Ipswich Council of strength of feeling. Results given to Ipswich BC. Proposal no longer in IBC plan. |
| 8.9 Leisure & Sport |  |  |  |  |  |
| Start Gardening Club | To meet wishes of residents. Good support for a number of new activities. | Residents Groups | Village Hall Trust | H | Up and running, Meetings in Village Hall first Tuesday of every month. |
| Start Rambling Club | To meet wishes of residents. | Residents Groups | Village Hall Trust | H | No progress. |
| Start Yoga and/or Keep Fit. | To meet wishes of residents | Residents Groups | Village Hall Trust | M | Yoga classes started. Every Wednesday Hall first Every Wednesday evening (beginners and advanced) in Village Hall |
| Facilitate Village Hall Trust on future development of Hall (Not Active) | Result of residents views on how Hall should be developed. | Village Hall Trust |  | M | Convey full list of comments from Questionnaire to Village Hall Trustees. |
| Organise Village Events | Request for more social activities | Events Committee | Village Hall Trust | M | A number of events have been successfully organised for the village. Events for 2007 -trip to wisley gardens -Jazz in the village paddock -Xmas show at Thursford -New Year party in Village Hall. |
| Investigate feasibility of a children’s playground (Not Active) | 41% of residents in favour of having a children’s playground | None |  | L | Profile shows there is probably not enough users to justify necessary research and cost. Currently there is no owner-keep on the back burner. |
| Start local tennis club. | Popular request from survey. Local private facilities exist. | Residents Group |  | M | Recently formed, initially using private facilities within the village. ACHIEVED |
| 8.10 Communication |  |  |  |  |  |
| Set up Village web site | To improve communication in the Village | Val Byrne | Village organisations Parish Council | M | Web site is now up and running (www.westerfield-village.co.uk) ACHIEVED |
| Produce residents’ pack. Produce local footpath map. | Popular request from survey Popular request for survey. | PCC Parish Council |  | H | Pack now complete and delivered to each household Pack is being updated by Sam Cowley. ##### ACHIEVED |
| Produce house name list | As above | Parish Council |  | H | ACHIEVED |
| Set up leaflet-drop network (Not Active) | Co-ordinate & improve efficiency for various groups. | Village Network | Village organisations | M | Currently not enough volunteers. Some form of networking already exists for different groups. |
| 8.11 Local Government |  |  |  |  |  |
| Review attendance of Annual Parish Meeting | Two thirds of residents have never attended. | Parish Council |  | M | .Some new ideas and suggestions (guest speaker, more of a social event etc) |
| Provide information to residents on Quality Status | Mentioned it in Parish Plan. | Parish Council |  | M | Presentation by SALC at recent parish council meeting. |
| Improve communication | 22% dissatisfied with information provided. | Parish Council |  | M |  |
| 8.12 Religion |  |  |  |  |  |
| Feed survey results back to PCC |  | Steering Group |  | H | #### ACHIEVED |
| Identify opportunities from plan | Survey identified some opportunities. | PCC | Residents. | H |  |

| 8.13 Young People’s Survey |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Investigate providing a focal point in village |  | Results of Youth Questionnaire | None |  |  | L |  |  |  |
| Provision of a playing field |  | Vast majority wanted this | None |  |  | L |  |  |  |
|  | ### Contacts: ### Parish Council |  |  | Yvonne Maynard |  |  | Tel: 212316 |  |  |
|  | ### Parochial Church Council |  |  | ### Judy Northfield |  |  | 230188 |  |  |
|  | Village Hall Trust |  |  | John Northfield |  |  | 255676 |  |  |
|  | Traffic & Safety Group |  |  | Peter Miller |  |  | 212316 |  |  |
|  | Events Group |  |  | Cynthia Reeve |  |  | 251843 |  |  |
|  | Environment Action Group |  |  |  |  |  |  |  |  |
|  | Village Web Site |  |  | Val Byrne |  |  | 251624 |  |  |

| Gardening Club | Judy Palmer | 259511 |
| --- | --- | --- |
| New Utility Services | Val Byrne | 251624 |
| Tennis Club | Bruce Doick | 252330 |
| Train & Maintenance Noise | Carole Easton | 287564 |